## Master Bug List
ID | Category | Severity | Priority | File / Component | Function / Lines | Bug Description | Impact | Recommended Fix | Status | Audit Verified
B-01 | Mobile File Routing | Critical | P0 | agents/backend.py | execute_sprint() L64–66 | Hardcoded `backend/` prefix filter — any non-Python project (React Native, Android, Go, ML) generates ZERO backend files with no error. | Mobile/multi-lang projects silently produce empty output. Root cause of 'files in wrong folder' bug. | Replace prefix filter with a project-type-aware router that maps mobile→app/, web→frontend/, python→backend/. | Open | —
B-02 | Mobile File Routing | Critical | P0 | agents/frontend.py | execute_sprint() L73–75 | Hardcoded `frontend/` prefix filter — React Native paths (app/, App.tsx) are dropped. FrontendDeveloperAgent produces zero files for mobile. | Mobile apps generate no frontend code at all. | Same as B-01: project-type-aware path routing for frontend agent. | Open | —
B-03 | Mobile File Routing | Critical | P0 | agents/backend.py | _file_system_prompt() L205–220 | System prompt hardcodes 'You are an expert Python/FastAPI backend developer' for ALL project types including Kotlin, Go, Rust, React Native. | LLM identity contradicts actual project tech stack — produces Python-style code for non-Python projects. | Inject project_type into system prompt and select language-specific persona dynamically. | Open | —
B-04 | Mobile File Routing | Critical | P0 | agents/frontend.py | _file_system_prompt() L262–276 | System prompt hardcodes 'React/TypeScript + Tailwind CSS' for ALL frontend types. Tailwind CSS is a web library incompatible with React Native. | Mobile apps get web-specific instructions causing className usage, wrong imports, and style API mismatches. | Detect project_type; inject NativeWind/StyleSheet instructions for mobile, Tailwind only for web. | Open | —
B-05 | Mobile File Routing | Critical | P0 | execution/ (missing step) | No scaffold step exists | No generation step creates mandatory React Native entry-point files: App.tsx, babel.config.js, tsconfig.json, metro.config.js. | Every generated mobile project is unrunnable without manual setup. User had to create 4 files manually. | Add a MobileScaffoldAgent or post-generation hook that writes required entry-point files for mobile projects. | Open | —
B-06 | Agent Connectivity | Critical | P0 | agents/backend.py | _generate_one_file() L92–145 | Assembled `context` parameter is accepted by execute_sprint() and passed to _generate_one_file() but NEVER forwarded to _build_file_prompt(). Context is silently discarded. | Architect output, design spec, intelligence layer, and predecessor message never reach the file-level LLM call. Each file is generated in isolation from the architecture. | Pass `context` into _build_file_prompt() and inject relevant sections (architecture summary, API contracts) into the per-file user prompt. | Open | CONFIRMED (BUG-BE01)
B-07 | Agent Connectivity | Critical | P0 | agents/frontend.py | _generate_one_file() L164–224 | Identical context-discard bug as B-06 in FrontendDeveloperAgent. | Frontend files are generated with no knowledge of backend API contracts, data models, or architecture decisions. | Same fix as B-06. | Open | CONFIRMED (BUG-NEW-3)
B-08 | Agent Connectivity | High | P1 | intelligence/context_orchestrator.py | _STAGE_NEEDS dict L17–34 | _STAGE_NEEDS for 'FrontendDeveloper' does not include 'backend' or 'BackendDeveloper'. Frontend agent never receives backend API contracts or generated model schemas. | Frontend fabricates API endpoints and data shapes independently from the backend implementation, causing integration failures. | Add 'backend' to _STAGE_NEEDS['FrontendDeveloper'] so the orchestrator injects backend artifacts into the frontend context package. | Open | —
B-09 | Agent Connectivity | Medium | P2 | workflow/engine.py | _record_message() L288–303 | WORKFLOW_MESSAGE_KEY is a single constant overwritten on every stage completion. Only the immediately preceding stage output is accessible via the predecessor channel. | BackendDeveloper's predecessor is SprintPlanner output, not the Architect's. Earlier stage outputs are unaddressable by later agents without going through ArtifactManager. | Store messages under stage-keyed keys (e.g., workflow_msg:{stage}) so any stage can retrieve any prior stage's output by name. | Open | —
B-10 | Agent Connectivity | Medium | P2 | workflow/context_budget.py | BackendDeveloper budget L178–189 | predecessor_max_chars=1000 for BackendDeveloper. Architect output is typically 4,000–8,000 chars. After truncation, only a fragment is received via the predecessor channel. | BackendDeveloper acts on a fragment of the architecture spec. Full architecture is only available via design key which stores the Designer's visual spec, not the Architect's technical spec. | Increase predecessor_max_chars to at least 4000 for Backend/Frontend, or store the Architect artifact under DESIGN_MEMORY_KEY separately from the visual design. | Open | —
B-11 | Agent Connectivity | High | P1 | workflow/context_assembler.py | _inject_sandbox_results() L527–561 | Method exists, is correctly implemented, but assemble() never calls it. BugAnalyst never receives actual lint/test/build results from the sandbox. | BugAnalyst has no empirical test data. It classifies bugs based solely on LLM inference, not actual test failures. | Call _inject_sandbox_results(project_id, stage_name, base) inside assemble() before _inject_template, matching existing enrichment pattern at lines 163–166. | Open | CONFIRMED (BUG-007/CA01)
B-12 | Module Versioning | High | P1 | All code-gen prompts | No version spec in any prompt | No prompt in the system specifies package versions, deprecated APIs, or forbidden imports for any technology. LLM uses stale training-data knowledge. | Generated code used: AsyncStorage from react-native (removed 2019), @react-navigation v6/v7 incompatibility, non-existent lucide icon 'Restaurant', React.lazy with React Navigation (unsupported). | Create a TechStackVersionRegistry with known-good versions per stack. Inject version constraints into code-gen system prompts before LLM call. | Open | —
B-13 | Module Versioning | High | P1 | workflow/pipeline_supervisor.py | _pin_dependencies() L1020–1055 | DependencyPinner runs post-generation and only resolves version ranges in manifest files. It cannot fix wrong API usage patterns, incompatible peer deps, or non-existent package exports. | Wrong imports (AsyncStorage) and incompatible peer dependencies (nav v6/v7) survive pinning unchanged and cause runtime failures. | Pinning must be complemented by a pre-generation version injection step. Post-generation pinning alone is insufficient. | Open | —
B-14 | Module Versioning | Medium | P2 | prompt/qa_builder.py | _MOBILE_SYSTEM_PROMPT L172 | QA test prompt correctly references @react-native-async-storage/async-storage (modern package). This knowledge exists in QA but not in code-gen prompts. | QA knows the correct modern packages but code generation doesn't — inconsistency between stages. | Extract correct package references from QA prompts into a shared TechStackVersionRegistry used by all agents. | Open | —
B-15 | QA Sandbox | High | P1 | execution/code_sandbox.py | SANDBOX_ENABLED env var | SANDBOX_ENABLED=false by default. CodeSandbox is fully implemented (install/lint/build/test for Python+Node) but never runs. Additionally _build_python() only py_compiles ONE entry-point file, leaving all other .py files unchecked. | Zero test execution for any project. Generated test files have never been run. No build validation. | Change default to SANDBOX_ENABLED=true. Fix _build_python() to compile all .py files. Add fallback for environments without Docker. | Open | CONFIRMED (BUG-SB01 — wider scope than expected)
B-16 | QA Sandbox | High | P1 | workflow/pipeline_supervisor.py | _run_sandbox() L630 / L843 | Sandbox runs post-sprint (before QA release stage). QA writes test files during the release phase AFTER all sprints. Those new test files are never executed. | QA-generated tests have never been run against the project. The QA stage produces a false signal of test coverage. | Add a sandbox execution call after the QA release stage completes, re-running with the newly written test files. | Open | —
B-17 | QA Sandbox | Medium | P2 | prompt/qa_builder.py | mobile branch file filter L238 | Mobile QA file filter keyword list includes 'calculator' and 'math'. _MOBILE_SYSTEM_PROMPT contains calculator-specific test file references (__tests__/calculator.test.ts, __tests__/memory.test.ts, __tests__/CalculatorScreen.test.tsx). | QA tests are written specifically for a calculator app for every mobile project. Non-calculator apps get test files for the wrong feature set. | Replace hardcoded calculator template with a project-type-aware dynamic QA prompt. Inject actual screen/service names from the file inventory. | Open | CONFIRMED (BUG-QA01 + BUG-QA02)
B-18 | Requirement Change | High | P1 | api/workflow.py | 4 change endpoints confirmed | PREVIOUSLY flagged as missing. Audit confirmed 4 requirement-change endpoints exist in api/workflow.py. However ChangeManager is still not injected into PipelineSupervisor (change_manager=None default) so the endpoints exist but the wiring is incomplete. | Endpoints exist but ChangeManager=None means changes are silently swallowed by the supervisor. The API surface is present but non-functional end-to-end. | Inject ChangeManager into PipelineSupervisor. Remove the None-check guard that swallows rollback requests. | Partially Fixed | NOT CONFIRMED (endpoints exist; wiring gap remains)
B-19 | Requirement Change | Critical | P0 | workflow/pipeline_supervisor.py | BugAnalyst rollback L762–769 | change_manager=None by default. When BugAnalyst triggers rollback, the code logs a warning and sets state=RESUMING_FROM_CHANGE without removing any stages from stages_completed. | Architecture-level bugs are silently swallowed. Pipeline 'succeeds' with stale/incorrect code. No stages are actually invalidated. | ChangeManager must be injected (not optional=None). Alternatively, implement inline rollback logic that removes affected stages from stages_completed when change_manager is absent. | Open | CONFIRMED (BUG-PS02 — no architectural context passed)
B-20 | Requirement Change | High | P1 | workflow/pipeline_supervisor.py | _run_impl() REPLANNING L278–334 | completed_sprints set is never modified during REPLANNING. Sprint loop skips any sprint already in completed_sprints, so requirement changes that affect sprint code are silently ignored. Also: release stages not cleared from stages_completed. | Requirement changes that should trigger sprint re-execution produce no effect. Workflow completes with stale generated code. | When ChangeManager.apply() runs, identify which sprint numbers are affected by the change and remove them from completed_sprints before re-running. | Open | CONFIRMED (BUG-PS01)
B-21 | Context Budget | Medium | P2 | workflow/context_budget.py | max_total_tokens — all budgets | max_total_tokens per-stage limits (e.g., qa:6000, backend:12000) are documented as advisory only and never enforced. Only StageRunner._trim_context_for_model() applies a single 600,000-char global cap. | Per-stage token intentions are ignored. QA or backend stages can assemble contexts far exceeding their stated budgets with no trimming applied. | Enforce max_total_tokens inside ContextAssembler.assemble() by trimming the assembled context string to budget.max_total_tokens * 4 chars before returning. | Open | —
B-22 | Data Integrity | High | P1 | memory/knowledge_memory.py | store() L171–173 | SQLite commit and HNSW index save are non-atomic. A crash between conn.commit() and _save_index() leaves the SQLite row written but the on-disk HNSW index without the vector. | On restart, search() can return label IDs with no matching HNSW entry (KeyError) or miss entries that are in SQLite. Knowledge store silently corrupts. | Wrap the write in a try/finally that rolls back the SQLite transaction if _save_index() raises. Or write HNSW to temp file and atomic-rename after SQLite commit. | Open | —
B-23 | Prompt Quality | Medium | P2 | prompt/backend_builder.py | BackendPromptBuilder L22–120 | BackendPromptBuilder is project-type-aware (has Python/ML, Android/Kotlin, Go, Rust sections) but is only used in _build_default_action(). The actual sprint execution path _generate_one_file() does NOT use BackendPromptBuilder. | The best project-type-aware backend prompt exists but is on a dead code path during sprint runs. All code generation uses the hardcoded Python/FastAPI prompt. | Refactor _file_system_prompt() in BackendDeveloperAgent to use BackendPromptBuilder.build_system_prompt(project_type) instead of a hardcoded string. | Open | —
B-24 | Prompt Quality | Medium | P2 | prompt/architect_builder.py | ARCHITECTURE SIZING RULES L122–158 | Sizing rules describe only web-tier infrastructure (FastAPI, PostgreSQL, Redis, CDN, load balancers). No rules for mobile, ML compute, or CLI packaging. | Mobile projects get recommended Redis and load balancers. ML projects get web-tier infrastructure. Architect produces irrelevant or harmful recommendations. | Add project-type-specific sizing sections: mobile (app store, push infra, offline storage), ML (GPU compute, dataset storage, training pipeline), CLI (packaging, distribution). | Open | —
B-25 | Prompt Quality | Medium | P2 | intelligence/context_orchestrator.py | _load_stage_artifacts() L347 | Architect artifact is truncated to 2,000 characters when loaded by ContextOrchestrator. A full architecture spec is typically 5,000–10,000 chars. | Code agents receive a fragment of the architecture. Critical API design and data model sections may be cut off. | Increase artifact truncation limit to at least 6,000 chars for the Architect artifact, or implement section-aware truncation that preserves API contracts. | Open | —
B-26 | Return Type | Low | P3 | workflow/context_assembler.py | _inject_template() L563 | Method return type annotation says tuple[str, bool] but implementation returns 4 values: (content, bool, str¦None, float¦None). Line 164 correctly unpacks 4 values. | Incorrect annotation misleads type checkers and maintainers. mypy/pyright will flag incorrect usage. | Fix the return type annotation to tuple[str, bool, str ¦ None, float ¦ None]. | Open | —
B-27 | Missing File | High | P1 | agents/frontend.py | import FrontendPromptBuilder L12 | frontend.py imports FrontendPromptBuilder from ..prompt.frontend_builder, but frontend_builder.py is absent from the codebase (not in uploaded snapshot or may be missing in repo). | Would cause ImportError when FrontendDeveloperAgent is instantiated, breaking all frontend code generation. | Create frontend_builder.py with FrontendPromptBuilder class, analogous to backend_builder.py with web/mobile/React Native persona variants. | Open | —
B-28 | Agent Connectivity | Medium | P2 | agents/agent_factory.py | create() — TechLead branch | AgentFactory.create() for TechLeadAgent never passes workspace_manager parameter. TechLeadAgent.__init__() receives workspace_manager=None, so the ArtifactStore write inside review() is always skipped. | Even when TechLeadAgent is eventually wired into the sprint pipeline, tech_review.json will never be written to the ArtifactStore. Review results exist only in memory and are lost. | Pass workspace_manager to TechLeadAgent constructor in AgentFactory.create(), matching the pattern used for other agents. | Open | BUG-NEW-1 (NEW)
B-29 | Context Budget | High | P1 | workflow/engine.py | _check_context_window() | _check_context_window() compares total_project_tokens (a cumulative counter across ALL prior stages) against a per-call context window limit. It does not check the current call's token count alone. | After a handful of stages, total_project_tokens permanently exceeds any per-call threshold. The engine falsely flags every subsequent stage as a context overflow even when the individual call is within limits. | Track current_call_tokens separately from total_project_tokens. Compare only current_call_tokens against the model's per-call context window limit. | Open | BUG-NEW-2 (NEW)
B-30 | Agent Connectivity | High | P1 | agents/frontend.py | execute_sprint() → _build_file_prompt() | execute_sprint() accepts a sprint_brief parameter but always passes "" (empty string) to _build_file_prompt(). The sprint scope is never injected into the per-file prompt for frontend files. | Frontend file generation has zero knowledge of sprint scope, acceptance criteria, or the specific feature being built. Each file is generated with no sprint context. | Pass the sprint_brief argument into _build_file_prompt() call site in execute_sprint(), identical fix to BUG-BE01 in BackendDeveloperAgent. | Open | BUG-NEW-3 (NEW)
B-31 | QA Sandbox | High | P1 | agents/qa.py (or equivalent) | run_sprint_qa() — dead code | QAAgent.run_sprint_qa() is implemented but is never called in sprint_executor.py or pipeline_supervisor.py. The sprint execution flow contains no QA step between dev agents and SandboxVerification. | No QA tests are generated per-sprint. The QA stage only fires during the Release phase, meaning dev work has no test gate. Sprint-level regressions go undetected. | Add a call to run_sprint_qa() in sprint_executor.py after the dev agents complete and before SandboxVerification. Wire the result to gate sandbox execution. | Open | BUG-NEW-4 (NEW)
B-32 | Prompt Quality | Medium | P2 | prompt/qa_builder.py | _build_mobile_prompt() | [CALLEE-UNVERIFIED] _build_mobile_prompt() returns a combined string with the system prompt prepended inline into the user prompt body rather than returning them as separate values for the system_prompt= parameter. | The LLM receives system instructions embedded in the user turn rather than the system role, reducing instruction-following reliability for mobile QA generation. | Refactor _build_mobile_prompt() to return (system_prompt, user_prompt) separately. Caller must pass system_prompt to generate_text(system_prompt=...) parameter. | Open | BUG-NEW-5 (NEW, CALLEE-UNVERIFIED)
B-33 | Prompt Quality | Medium | P2 | prompt/qa_builder.py | _WEB_SYSTEM_PROMPT | _WEB_SYSTEM_PROMPT hardcodes `from backend.main import create_app` and `/api/v1/auth/register` — FastAPI-specific patterns that do not exist in Django, Express.js, Go, or Rails projects. | Web QA tests for non-FastAPI projects fail at import time (no create_app factory) and test against a non-existent auth endpoint. All web QA tests for non-FastAPI stacks are broken from the start. | Make test setup patterns configurable by web framework. Detect framework from blueprint and inject the correct app factory import and auth endpoint pattern per project. | Open | BUG-NEW-6 (NEW)

## By Category
Category | Total | Critical | High | Medium | Low | Top Priority Bug
Mobile File Routing | 5 | 5 | 0 | 0 | 0 | Hardcoded `backend/` prefix filter — any non-Python project (React Native, Andro
Agent Connectivity | 8 | 2 | 3 | 3 | 0 | Assembled `context` parameter is accepted by execute_sprint() and passed to _gen
Module Versioning | 3 | 0 | 2 | 1 | 0
QA Sandbox | 4 | 0 | 3 | 1 | 0
Requirement Change | 3 | 1 | 2 | 0 | 0 | change_manager=None by default. When BugAnalyst triggers rollback, the code logs
Context Budget | 2 | 0 | 1 | 1 | 0
Data Integrity | 1 | 0 | 1 | 0 | 0
Prompt Quality | 5 | 0 | 0 | 5 | 0
Return Type | 1 | 0 | 0 | 0 | 1
Missing File | 1 | 0 | 1 | 0 | 0

## Priority Roadmap
Sprint | Priority | Bug IDs | Area | What To Build | Effort | Unblocks
Sprint 1 | P0 | B-01,B-02,B-03,B-04 | Mobile File Routing | Replace hardcoded backend/ and frontend/ prefix filters with project-type-aware path routing. Fix system prompt personas to be language/framework aware. | Large | Enables all non-Python projects to generate code
Sprint 1 | P0 | B-05 | Mobile Scaffold | Add MobileScaffoldStep that generates App.tsx, babel.config.js, tsconfig.json, metro.config.js for React Native projects automatically. | Medium | Every mobile project runnable out-of-the-box
Sprint 1 | P0 | B-19 | ChangeManager Wiring | Inject ChangeManager into PipelineSupervisor. Remove change_manager=None guard that silently swallows rollbacks. B-18 endpoints already exist in api/workflow.py. | Medium | Requirement change API becomes functional end-to-end
Sprint 2 | P0 | B-06,B-07,B-30 | Agent Connectivity | Pass assembled context + sprint_brief into _build_file_prompt() in BackendDeveloperAgent and FrontendDeveloperAgent. Inject architecture summary, API contracts, sprint scope into per-file prompts. | Large | Architecture decisions actually influence generated code
Sprint 2 | P0 | B-20 | REPLANNING Sprint Invalidation | Fix REPLANNING block to clear affected sprint numbers from completed_sprints. Clear release stages from stages_completed when resuming. | Medium | Requirement changes actually trigger re-generation
Sprint 3 | P1 | B-29 | Context Window Check Fix | Fix _check_context_window() to compare current call's token count, not cumulative project total. Track current_call_tokens separately. | Small | No false context-overflow errors mid-pipeline
Sprint 3 | P1 | B-12,B-13 | Module Versioning | Create TechStackVersionRegistry with known-good package versions per stack. Inject version constraints into code-gen system prompts before LLM call. | Medium | No more deprecated API usage in generated code
Sprint 3 | P1 | B-15,B-16 | QA Sandbox Execution | Enable SANDBOX_ENABLED=true by default. Fix _build_python() to compile all .py files. Add sandbox run call after QA release stage with the newly written test files. | Medium | Generated tests actually run
Sprint 3 | P1 | B-31 | Sprint QA Wiring | Wire QAAgent.run_sprint_qa() into sprint_executor.py after dev agents complete. Gate SandboxVerification on QA completion. | Medium | Per-sprint QA runs; dev work has a test gate
Sprint 4 | P1 | B-08 | Frontend←Backend Context | Add 'backend' to _STAGE_NEEDS['FrontendDeveloper'] in context_orchestrator.py so backend API contracts are available to frontend agent. | Small | Frontend generates correct API calls
Sprint 4 | P1 | B-11 | Sandbox→BugAnalyst | Call _inject_sandbox_results() inside context_assembler.assemble(). BugAnalyst receives actual test output. | Small | BugAnalyst operates on real test failures
Sprint 4 | P1 | B-22 | Knowledge Memory Integrity | Make SQLite+HNSW writes atomic. Write HNSW to temp file, atomic-rename after SQLite commit. Add consistency check on startup. | Medium | Knowledge store cannot corrupt on crash
Sprint 4 | P1 | B-27 | FrontendPromptBuilder | Create frontend_builder.py with FrontendPromptBuilder. Add web/mobile/React Native persona variants mirroring backend_builder.py. | Medium | FrontendDeveloperAgent can instantiate without ImportError
Sprint 5 | P1 | B-28 | TechLead ArtifactStore Wiring | Pass workspace_manager to TechLeadAgent constructor in AgentFactory.create(). Then wire TechLeadAgent.review() into sprint_executor.py after dev agents. | Medium | TechLead review artifacts are actually persisted; dead code becomes live
Sprint 5 | P2 | B-21 | Context Budget Enforcement | Enforce max_total_tokens in ContextAssembler.assemble() by trimming assembled context to budget limit before returning. | Small | Per-stage token budgets are actually respected
Sprint 5 | P2 | B-09,B-10 | Predecessor Channel | Store messages under stage-keyed keys. Increase predecessor_max_chars for Backend/Frontend to at least 4000. | Small | Agents can access any prior stage output by name
Sprint 5 | P2 | B-23,B-24,B-25 | Prompt Quality | Wire BackendPromptBuilder into _file_system_prompt(). Add mobile/ML sizing rules to ArchitectBuilder. Increase artifact truncation limit. | Medium | Better prompts produce better code across all project types
Sprint 6 | P2 | B-32,B-33 | QA Prompt Fixes | Fix _build_mobile_prompt() to return separate (system, user) prompts. Make _WEB_SYSTEM_PROMPT framework-aware instead of hardcoding FastAPI paths. | Small | Web+mobile QA works for non-FastAPI / non-calculator projects
Sprint 6 | P3 | B-17,B-26 | Polish | Fix mobile QA keyword filter to be project-aware. Fix _inject_template() return type annotation. | Small | QA tests cover all mobile screens; type safety improved

## Architecture Violations
Principle Violated | Bug ID | File | Description | Fix
Agents communicate only through artifacts and memory | B-06, B-07, B-30 | agents/backend.py, agents/frontend.py | Assembled context (which carries all inter-agent communication) is silently discarded inside _generate_one_file(). sprint_brief is also always empty. Files generated in isolation. | Forward context + sprint_brief into _build_file_prompt(); inject architecture and predecessor artifacts explicitly.
Every stage produces structured artifacts | B-11, B-28, B-31 | workflow/context_assembler.py; agents/agent_factory.py; agents/qa.py | _inject_sandbox_results() never called so sandbox artifacts never reach BugAnalyst. TechLead review() never writes to ArtifactStore (workspace_manager=None). QA run_sprint_qa() never called so sprint QA artifacts never exist. | Call _inject_sandbox_results() in assemble(); inject workspace_manager into TechLeadAgent; call run_sprint_qa() in sprint_executor.
Workflow Engine is the only orchestrator | B-19 | workflow/pipeline_supervisor.py L762–769 | No API endpoint triggers the ChangeManager → PipelineSupervisor re-run flow. The orchestration entry point for requirement changes does not exist. | Add requirement-change endpoint that calls the workflow engine, not any agent directly.
Reviewer approves every stage | B-19 | workflow/pipeline_supervisor.py L762–769 | When change_manager=None, BugAnalyst's rollback request is silently ignored. Stages are not invalidated, no reviewer re-run triggered. | ChangeManager must not be optional. Inject it properly and ensure rollback always invalidates the correct stages.
Context Builder constructs context | B-09, B-29 | workflow/engine.py L288–303 | WORKFLOW_MESSAGE_KEY overwrites the same key each stage. _check_context_window() checks cumulative project tokens rather than the current call's token count. | Store per-stage messages under stage-keyed memory slots. Fix context window check to use per-call token count.
Memory Manager stores and retrieves memory | B-22 | memory/knowledge_memory.py L171–173 | Non-atomic SQLite+HNSW writes can leave memory in a corrupt state after a crash. Memory Manager's durability guarantee is broken. | Atomic write pattern: HNSW to temp file + rename after SQLite commit.
No direct agent-to-agent communication | B-08 | intelligence/context_orchestrator.py L17–34 | _STAGE_NEEDS omits backend output for FrontendDeveloper. Frontend must infer API contracts from the Architect spec rather than actual backend output, creating implicit coupling through hallucination. | Add 'backend' to FrontendDeveloper's _STAGE_NEEDS so the ContextOrchestrator (not a direct call) provides backend artifacts.
Execution Engine is the only component allowed to modify project files | B-01, B-02 | agents/backend.py, agents/frontend.py | BackendDeveloperAgent and FrontendDeveloperAgent write files directly. The prefix filter bug means they write to wrong paths or write nothing — with no centralised path validation. | Route all file writes through a central FileRouter that validates and normalises output paths before writing.
Stateless agents | B-28 | agents/agent_factory.py | AgentFactory never injects workspace_manager into TechLeadAgent, creating a permanent None-state dependency. The agent's write path silently degrades based on missing injection. | All agent dependencies must be injected via factory. No agent should degrade silently due to missing injections — fail fast at construction time.

## Audit Results
AI DevOS — Full Codebase Audit Results ¦ August 2026
Pre-Tag ID | Excel Ref | Component | Audit Verdict | Code Evidence | Notes
BUG-007 / CA01 | B-11 | context_assembler.py | CONFIRMED | assemble() calls _inject_gate_feedback() and _inject_template() — _inject_sandbox_results() is never called. | _inject_sandbox_results() fully implemented at L590–624 but orphaned.
BUG-BE01 | B-06 | agents/backend.py | CONFIRMED | _generate_one_file() never passes context/sprint_brief to _build_file_prompt(). sprint_brief argument is always ''. | Identical pattern also confirmed in FrontendDeveloperAgent (BUG-NEW-3 / B-30).
BUG-QA01 | B-17 | prompt/qa_builder.py | CONFIRMED | _MOBILE_SYSTEM_PROMPT contains: __tests__/calculator.test.ts, __tests__/memory.test.ts, __tests__/CalculatorScreen.test.tsx. | Calculator-specific test template used for every mobile project regardless of type.
BUG-QA02 | B-17 | prompt/qa_builder.py | CONFIRMED | _build_web_prompt() priority files: backend/main.py, backend/routers/auth.py, backend/models/user.py, backend/schemas/user.py, backend/config.py, backend/database.py — all hardcoded. | These paths only exist in FastAPI projects. All other web frameworks get wrong priority files.
BUG-TL01 | (none) | agents/tech_lead.py | CONFIRMED | Sprint execution order: ScrumMaster→SprintDelta→FileStructurePlanner→BackendDev+FrontendDev→SandboxVerification→SprintDeploy→SprintReview. TechLeadAgent absent. | TechLeadAgent fully implemented but zero references in sprint_executor.py or pipeline_supervisor.py.
BUG-TL02 | (none) | agents/tech_lead.py | CONFIRMED | After structured = self.extract_json(response.content): only stamps iteration and approved defaults. No logic to force approved=False when critical violations exist. | LLM can return approved=True with critical violations and the agent will pass it through unchanged.
BUG-SB01 | B-15 | execution/code_sandbox.py | CONFIRMED (wider scope) | SANDBOX_ENABLED=false disables syntax_check(). Additionally _build_python() only py_compiles ONE entry-point file. | Scope is wider than originally tracked: not just disabled, but also incomplete when enabled.
BUG-PS01 | B-20 | workflow/pipeline_supervisor.py | CONFIRMED | REPLANNING block sets state=ALL_SPRINTS_COMPLETE and calls _clear_release_stages() — but stages_completed is not filtered to remove release stage entries before resuming. | Release stages re-run but are pre-marked as completed so they are skipped.
BUG-PS02 | B-19 | workflow/pipeline_supervisor.py | CONFIRMED | engine.run() called with content=f'A bug was found. Your task is to apply the following fix: {fix}' — no blueprint, no architecture context, no sprint plan. | BugAnalyst applies fixes blind — no architectural constraints to guide the fix.
BUG-009 | (none) | workflow/stage_runner.py | NOT CONFIRMED | _build_retry_context(original, feedback, attempt) uses LATEST feedback appended to ORIGINAL context — not accumulated across all retries. | Retry context does NOT compound. Each retry replaces the previous feedback with the latest only.
GAP-AR01 | (none) | prompt/architect_builder.py | NOT CONFIRMED (already implemented) | SYSTEM_PROMPT already requests: folder_structure, dependencies (with version fields), entry_points, constraints. | All blueprint fields were already in the architect output instructions. No gap exists.
GAP-MEM01 | (none) | memory/blueprint_store.py | NOT CONFIRMED (already implemented) | blueprint_store.py exists (8,290 bytes). Three-layer implementation: disk (blueprint.json) + MemoryManager KV + LearningLoop SQLite. | BlueprintStore fully implemented. Wiring gap remains: PipelineSupervisor.__init__() does not accept blueprint_store parameter.
GAP-API01 | B-18 | api/workflow.py | NOT CONFIRMED (already implemented) | 4 requirement-change endpoints confirmed in api/workflow.py. | Endpoints exist. Wiring gap remains: ChangeManager=None in PipelineSupervisor swallows change requests. B-18 updated to Partially Fixed.
NEW BUGS FOUND DURING AUDIT — August 2026
Bug ID | Excel Ref | Component | Severity | Code Evidence | Impact
BUG-NEW-1 | B-28 | agents/agent_factory.py | Medium | TechLeadAgent created with workspace_manager=None — ArtifactStore write permanently skipped. | tech_review.json never written even when TechLead is eventually wired in.
BUG-NEW-2 | B-29 | workflow/engine.py | High | _check_context_window() uses total_project_tokens (cumulative) vs per-call limit. | False context-overflow errors after a few pipeline stages; may abort valid runs.
BUG-NEW-3 | B-30 | agents/frontend.py | High | execute_sprint() passes sprint_brief='' to _build_file_prompt() — identical to BUG-BE01. | Frontend sprint generation has no sprint scope; all files generated context-free.
BUG-NEW-4 | B-31 | agents/qa.py | High | QAAgent.run_sprint_qa() implemented but never called in sprint_executor or supervisor. | No per-sprint QA. Dev work has zero test gate throughout sprint loop.
BUG-NEW-5 | B-32 | prompt/qa_builder.py | Medium | [CALLEE-UNVERIFIED] _build_mobile_prompt() may prepend system prompt into user message body. | System instructions sent in wrong role; reduces mobile QA instruction adherence.
BUG-NEW-6 | B-33 | prompt/qa_builder.py | Medium | _WEB_SYSTEM_PROMPT hardcodes `from backend.main import create_app` and `/api/v1/auth/register`. | Web QA for non-FastAPI projects fails at import time and tests wrong endpoint.
PREVIOUSLY ASSUMED GAPS — ALREADY IMPLEMENTED (No Action Required)
Gap ID | Finding | Conclusion
GAP-AR01 | architect_builder.py already outputs folder_structure, dependencies (with versions), entry_points, constraints in system prompt OUTPUT RULES section. | No change needed to architect_builder.py.
GAP-MEM01 | blueprint_store.py exists with three-layer persistence: disk + MemoryManager KV + LearningLoop SQLite. | Wiring gap only: PipelineSupervisor needs blueprint_store injected.
GAP-API01 | 4 requirement-change endpoints confirmed in api/workflow.py. | Wiring gap only: ChangeManager=None in PipelineSupervisor (tracked as B-18/B-19).
BUG-009 | Retry context does NOT compound. _build_retry_context() uses original context + LATEST feedback only. | No fix needed for retry logic.

## Summary Dashboard
AI DevOS — Bug Audit Dashboard ¦ August 2026 ¦ 33 Bugs Tracked
| TOTAL TRACKED | CRITICAL | HIGH | MEDIUM | LOW | NEW (Audit) | CONFIRMED
| 33 | 8 | 13 | 11 | 1 | 7 | 7
AUGUST 2026 FULL AUDIT — SUMMARY
| 9 of 13 | Pre-tagged bugs CONFIRMED by code audit | See Audit Results sheet for evidence quotes
| 4 of 13 | Pre-tagged items NOT CONFIRMED (already done) | GAP-AR01, GAP-MEM01, GAP-API01, BUG-009 all implemented
| 6 NEW | New bugs found during audit | B-28 through B-33 — added to Master Bug List
| 1 | Bug reclassified (B-18) | No endpoint → Partially Fixed (endpoints exist, wiring broken)
TOP RISKS — FIX BEFORE NEXT RELEASE
| B-01/02 | Mobile file agents produce zero files | Every generated mobile project is empty/broken
| B-06/07/30 | Context + sprint_brief discarded in file generation | Architecture spec + sprint scope never reach code LLM
| B-19/20 | ChangeManager=None; REPLANNING skips affected sprints | Requirement changes never actually re-run code generation
| B-29 | _check_context_window uses cumulative vs per-call tokens | False overflow errors abort valid pipeline runs mid-way
| B-31 | QAAgent.run_sprint_qa() is dead code | Zero per-sprint QA; dev work has no test gate whatsoever
| B-12 | No package version awareness in any code-gen prompt | Deprecated APIs, incompatible versions in every project